## Cost & Schedule Checklist
Project Cost and Schedule Checklist
The Project Cost and Schedule is the official budget and timeline for the project. Tasks 1-6 outlined in the Project Cost and Schedule are for illustrative purposes only. The Cost and Schedule must be consistent with the Grant Application Cover Sheet. Applications with missing components will be at a competitive disadvantage.
Project Cost and Schedule
(x) | Ensure these items are completed prior to submitting to Caltrans
Use the Fiscal Year 2021-22 template provided (do not alter the template).
List all tasks with the same title as stated in the Scope of Work.
Include task numbers in proper sequencing, consistent with the Scope of Work.
Ensure that sub-task numbers are not included.
Task 01 is a required task. It must be titled "Project Administration", it cannot exceed 5% of the grant amount requested, and only the grantee can charge against this Task. This Task must only include the following activities and deliverables: •Project kick-off meeting between the grantee and Caltrans at the start of the grant • Invoicing and quarterly reporting to Caltrans • DBE Reporting (federal grants only)
Include Task 02 for procurement of consultants, if consultants are needed. This task is for the grantee only.
Complete all budget columns as appropriate: Total Cost, Grant Amount, Local Cash Match, and if applicable, Local In-Kind Match.
Ensure the correct minimum local match amount, calculated as a percentage of the total project cost (grant plus local match), is provided.
The total Local Match amount must meet the minimum required Local Match for the specified Grant Category
Each task must include a grant amount and local match amount (excluding Tasks 01 and 02).
Identify if a Tapered Local Match appraoch will be used, which allows grantees to vary the required local match ratio over the life of the grant contract. Grantee agees to satisfy the total local match amount by the contract expiration date.
Identify the estimated indirect cost rate if indirect costs will be reimbursed. If FY 2021-22 indirect cost rates are not available, the rate will be an estimate based on the currently approved rate.
Include a best estimate of the amount of time needed to complete each task.
State a realistic total cost for each task based on the work that will be completed.
Start the timeframe at the beginning of the grant period (July 2021 for MPO/RTPAs; October/November 2021 for non-MPO/RTPAs).
Extend the timeframe to the end of the grant period (Project end dates differ based on applicant type (MPO/RTPA or non-MPO/RTPA) and type of funds (State or federal). See Grant Application Guide, Chapter 8.2, for more details).

## Sample Cost & Schedule
California Department of Transportation Sustainable Transportation Planning Grant Program PROJECT COST AND SCHEDULE
Grant Category DROP DOWN MENU
Grant Category | [40 empty] | Sustainable Communities Competitive (11.47% match)
Grant Fiscal Year | [40 empty] | Sustainable Communities Competitive - Technical (11.47% match)
Project Title | [40 empty] | Strategic Partnerships Transit - FTA 5304 (11.47% match)
Organization (legal name) | [40 empty] | Strategic Partnerships - FHWA SPR Part I (20% match)
Task # | Task Title | Estimated Grant Amount* | Estimated Local Cash Match* | Estimated Local In-Kind Match* | Estimated Total Project Cost* | FY 2021/22 | [10 empty] | FY 2022/23 | [11 empty] | FY 2023/24 | [11 empty] | Grant Fiscal Year DROP DOWN MENU
[6 empty] | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | FY 2020-21
01 | Project Administration (no more than 5% of total Grant Award) | 0 | 2500 | 0 | 2500
02 | Consultant Procurement | 4427 | 574 | 0 | 5000
1 | Existing Conditions | 11509 | 1491 | 0 | 13000
2 | Analysis | 30986 | 4015 | 0 | 32500
3 | Public Outreach | 39839 | 5162 | 0 | 45000
4 | Advisory Committee Meetings | 13280 | 1721 | 0 | 15000
5 | Draft and Final Plan | 72595 | 6577 | 0 | 82000
6 | Board Review/Approval | 4424 | 900 | 0 | 5000
Totals |  | 177060 | 22940 | 0 | 200000
* Use only whole dollars in the financial information fields. Dollar amounts must be rounded up/down and decimals should not be shown.
Does your agency plan to request reimburesement for indirect costs? |  |  | If yes, what is the estimated indirect cost rate?
Does your agency plan to use the Tapered Match approach for invoicing purposes?
Yes
No
Yes
No